INTERNATIONAL CYBERSECURITY AND DIGITAL FORENSICS ACADEMY

(ICDFA)

Governance, Risk and Compliance (GRC) 205

Business Continuity and Disaster Recovery Planning

STUDENT NAME: OVAT CYRIL GIFT

REG. NO:  2025/GCR/12877

WORD COUNT: 3802
DATE: 24/10/2026

Contents

Executive Summary	3

Task 1: Business Impact Analysis (BIA)	3

1.1 Five-Function BIA	3

1.2 Worked Impact Calculations	4

Task 2: Recovery Objectives and Backup Design	5

2.1 Recovery Objective Matrix	5

2.2 Checkpoint Calculations at 08:00	5

2.3 Backup and Restoration Design	6

Task 3: Recovery Strategy and Budget	6

3.1 Strategy Option Matrix & Budget	6

3.2 Recommendation and Justification	6

3.3 Comparison and ROI	7

Task 4: Business Continuity and Disaster Recovery Plan	7

4.1 Scope, Activation, and Roles	7

4.2 RACI Matrix	7

4.3 Temporary Procedures 72-Hour Outage	8

4.4 DR Runbook	8

4.5 Stakeholder Communication & Learner Notice	8

4.6 Return to Primary Site	9

5.1 Modelled Baseline Schedule 2 Technicians	9

5.3 Corrective Actions	10

Task 6: Governance and Performance Measures	10

6.1 Plan Ownership and Approval	10

6.3 Framework Alignment: NIST SP 800-34 and ISO 22301	11

6.4 Climate and Flood Consideration	12

6.5 Key Performance Indicators (KPIs)	12

6.6 BC/DR Maturity Assessment	13

References	13

GRC205 Business Continuity and Disaster Recovery Assignment

# Northbridge Skills Institute Business Continuity and Disaster Recovery Report

# Executive Summary

As the Business Continuity and Disaster Recovery Manager for Northbridge Skills Institute, this report details the comprehensive Business Continuity and Disaster Recovery (BC/DR) strategy developed in response to a 72-hour site outage caused by flooding and power failure. The assessment covers a Business Impact Analysis (BIA), recovery objective definitions, strategy selection, a coordinated BC/DR plan, schedule validation, and governance framework. Key recommendations include adopting a Warm Site strategy with independent, immutable backups and implementing manual workarounds to ensure a critical 11:00 examination proceeds with minimal disruption.

## Task 1: Business Impact Analysis (BIA)

### 1.1 Five-Function BIA

The BIA identifies the critical functions, dependencies, and minimum acceptable service levels for Northbridge Skills Institute.

| Function and Systems | Owner Role | Users Affected | Critical Resources / Dependencies | Impact Over Time | Minimum Acceptable Service and Controls | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| F1: Teaching & Assessment (LMS01, DB01) | Dean of Academics | 1,800 learners, 90 staff | Recovery network, AUTH01, DB01, LMS01; 25 workstations; BYOD; Invigilators | Immediate. 11:00 exam trigger adds NGN 120k; NGN 60k/hr. Loss of integrity, reputation. | Secure delivery of the 11:00 exam. Manual Process: 25 centre workstations for 40 learners (split into two cohorts), 80 BYOD via M365 Teams/Forms. Manual ID checks, secure browser locking, physical invigilation, and signed integrity declarations. | 1 |
| F2: Fees & Finance (FIN01, DB01) | Finance Director | Finance team, 1,800 learners | Recovery network, AUTH01, DB01, FIN01; Payment provider; Bank portals | 16:00 Day 0 deadline. NGN 40k/hr. Reconciliation delays, financial discrepancies. | Fee confirmation by 16:00. Manual Process: Extract provider transaction logs via external portal. Log manual receipts sequentially in a password-protected spreadsheet. Dual-authorization for refunds/updates. | 2 |
| F3: Admissions & Reg. (REG01, DB01) | Registrar | Prospective students, staff | Recovery network, AUTH01, DB01, REG01 | 18:00 Day 0 deadline. NGN 20k/hr. Delayed onboarding, lost revenue. | Intake applications by 18:00. Manual Process: Paper application forms or secure offline digital forms. Timestamp receipt, issue manual tracking numbers, and restrict access to PII. | 3 |
| F4: Staff Payroll (HR01, DB01) | HR Director | 90 staff | Recovery network, AUTH01, DB01, HR01; Bank submission portal | 12:00 Day 1 deadline. NGN 10k/hr. Staff dissatisfaction, manual corrections. | Payroll bank submission by 12:00 Day 1. Manual Process: Use last month's verified payroll data for fixed salaries. Manually calculate verified overtime/allowances. Dual-sign off by HR and Finance Directors. | 4 |
| F5: Records & Certs. (FS01, DB01) | Records Manager | Alumni, current learners | Recovery network, AUTH01, FS01 | 48-hour commitment. NGN 5k/hr. Regulatory/audit issues, reputational damage. | 48-hour service. Manual Process: Log requests manually. Issue provisional electronic letters signed by the Registrar, noting records will be formally dispatched upon system recovery. Maintain strict confidentiality. | 5 |

People, Premises, Suppliers, Information: All functions require secure alternate premises (25 workstations), staff availability, and communication (M365). Suppliers include the external payment provider and banking institutions. Information needs include secure access to M365 identities and manual record-keeping templates.

### 1.2 Worked Impact Calculations

Based on the supplied rates, assuming no recovery or continuity measures are activated:

- 8-Hour Impact:

  - F1: (NGN 60,000 × 8) + NGN 120,000 (exam trigger) = NGN 600,000

  - F2: NGN 40,000 × 8 = NGN 320,000

  - F3: NGN 20,000 × 8 = NGN 160,000

  - F4: NGN 10,000 × 8 = NGN 80,000

  - F5: NGN 5,000 × 8 = NGN 40,000

  - Total 8-Hour Cost: NGN 1,200,000

- 24-Hour Impact:

  - F1: (NGN 60,000 × 24) + NGN 120,000 = NGN 1,560,000

  - F2: NGN 40,000 × 24 = NGN 960,000

  - F3: NGN 20,000 × 24 = NGN 480,000

  - F4: NGN 10,000 × 24 = NGN 240,000

  - F5: NGN 5,000 × 24 = NGN 120,000

Total 24-Hour Cost: NGN 3,360,000

Limitations:

- These estimates assume static, linear disruption and do not account for cascading failures.

- The financial figures do not capture intangible losses such as reputational damage, long-term loss of learner trust, or the psychological impact on staff, which could exceed direct financial costs.

Priorities: The 11:00 examination makes F1 the highest business priority. However, the technical restoration order is dictated by shared infrastructure dependencies. The recovery network must be restored first, followed by AUTH01 (identity), security checks, DB01 (shared database), and finally the individual applications (LMS01, FIN01, etc.).

Dependency Risks:

- Single Point of Failure: DB01 supports F1-F4. If DB01 restoration fails, all four functions will be down.

- Identity Compromise: AUTH01 being a separate local directory poses a risk if synchronisation with M365 is lost or if it is compromised.

# Task 2: Recovery Objectives and Backup Design

### 2.1 Recovery Objective Matrix

- RTO Maximum acceptable time to restore a function after disruption.

- RPO Maximum acceptable amount of data lost, measured in time.

- MTD The absolute limit before irreparable business harm occurs (RTO + recovery buffer).

| Function | RTO Target | RPO Target | MTD | Justification |
| --- | --- | --- | --- | --- |
| F1 | 2.5 hours | 1 hour | 3 hours | Exam starts at 11:00 (3 hours post-incident). A 30-min buffer is needed between technical recovery and business validation. |
| F2 | 6 hours | 4 hours | 8 hours | Deadline at 16:00. Needs time for manual reconciliation before the deadline. |
| F3 | 8 hours | 4 hours | 10 hours | Deadline at 18:00. |
| F4 | 24 hours | 12 hours | 28 hours | Deadline 12:00 Day 1. Allows overnight recovery. |
| F5 | 48 hours | 24 hours | 72 hours | 48-hour internal service commitment allows for delayed recovery. |

### 2.2 Checkpoint Calculations at 08:00

- DB01 (B02): 07:00 Day 0 checkpoint. Age at 08:00 = 1 hour. Affects F1, F2, F3, F4.

- AUTH01 (B03): 00:00 Day 0 checkpoint. Age at 08:00 = 8 hours. Affects all functions.

- FS01 (B04): 23:00 Day -1 checkpoint. Age at 08:00 = 9 hours. Affects F5.

Mapping to RPOs:
DB01 meets the 1-hour RPO. FS01meets the 24-hour RPO. However, AUTH01 has an 8-hour data-loss window, which is a significant gap for F1's 1-hour RPO. Any AUTH01 changes made between midnight and 08:00 cannot be assumed recoverable. Manual records must be reconciled post-recovery.

### 2.3 Backup and Restoration Design

To address the gaps and the identified weaknesses:

- DB01 Chain: B01 (Full, 23:00 D-1) + B02 (Incremental, 07:00 D0). We will move to hourly incremental backups for DB01 to meet the 1-hour RPO.

- 3-2-1 Rule: Maintain 3 copies of data (Production, local backup, offsite).

- Immutable Offline Copy: The disconnected full backup must be migrated to an immutable, air-gapped cloud storage vault.

- Access Independence: Separate admin identities for production and backup environments. Enforce MFA and Just-In-Time access.

- Integrity & Usability: Offsite storage alone is insufficient; it must be tested. We will conduct quarterly automated restoration tests into a sandbox environment to verify data integrity and application usability, documenting unverified assumptions. Encryption keys must be stored separately from the backups.

# Task 3: Recovery Strategy and Budget

### 3.1 Strategy Option Matrix & Budget

Annual Planning Limit: NGN 3,000,000
Required Add-ons: NGN 400,000 (Protected backups) + NGN 200,000 (Training/Tests) = NGN 600,000.

| Package | Base Cost | Add-ons | Total Annual Cost | First Critical Service Est. | Data-Loss Window | Budget Fit? |
| --- | --- | --- | --- | --- | --- | --- |
| Cold | 600,000 | 600,000 | 1,200,000 | 24 - 48 hours | Up to 24 hours | Yes |
| Warm | 1,500,000 | 600,000 | 2,100,000 | 3 - 5 hours | 1 - 6 hours | Yes |
| Hot | 2,400,000 | 600,000 | 3,000,000 | ~ 1 hour | Up to 15 minutes | Exactly at limit |

### 3.2 Recommendation and Justification

Recommendation: The warm site of NGN 2,100,000 is recommended.

- Justification: The Cold site fails to meet our RTO for F1 (exam) and F2 (finance), resulting in massive disruption costs. The Hot site consumes the entire budget (NGN 3,000,000), leaving zero contingency funds for unplanned vendor fee increases. The Warm site fits comfortably within the budget and meets the RTO/RPO for F2-F5.

- Trade-offs & Unmet Objectives: The Warm site RTO is 3-5 hours, meaning F1's 2.5-hour RTO for the exam cannot be met technically. We must rely on the continuity workaround (M365/BYOD/manual invigilation) to bridge this gap.

- Residual Risks: The risk of missing the exam start time if the Warm site fails. This must be accepted by the Dean of Academics and the COO.

### 3.3 Comparison and ROI

An 8-hour disruption costs NGN 1,200,000; a 24-hour disruption costs NGN 3,360,000. The Warm site costs NGN 2,100,000 annually. A single 24-hour outage avoided pays for the strategy. However, a single-outage estimate cannot establish annual ROI because it ignores the probability of the disaster occurring. To approve expenditure and accept supplier claims, we need evidence such as historical flood data for the region, the provider's audited SOC 2 Type II report, and proof of successful recovery drills from similar educational institutions.

# Task 4: Business Continuity and Disaster Recovery Plan

### 4.1 Scope, Activation, and Roles

- Scope: Northbridge Main Site, all local systems- LMS01, FIN01, REG01, HR01, FS01, AUTH01, DB01.

- Activation Threshold: Any disruption exceeding 2 hours affecting critical infrastructure or life-safety.

- Decision Maker: IT/IR Manager (Primary), COO (Deputy).

- Coordination: The Incident Response (IR) team secures the perimeter and investigates potential cyber vectors e.g., if the power failure was caused by a deliberate grid attack or if a cyberattack is discovered during recovery. The Technical Recovery Team (2 technicians) handles infrastructure. Facility team manage the alternate site. The Continuity Team executes manual workarounds.

### 4.2 RACI Matrix

| Activity | BC/DR Manager | COO | Facilities | Technical Team | Business Coordinators | IR Team |
| --- | --- | --- | --- | --- | --- | --- |
| Plan Activation | A/R | C | I | I | I | I |
| Temporary Assessment | C | A | I | I | R | I |
| Backup Validation | A | I | - | R | I | C - Integrity check |
| System Restoration | A | I | I | R | I | C |
| Stakeholder Comms | R | A | I | I | C | C |
| Return to Primary Site | R | A | C | R | I | I |

### 4.3 Temporary Procedures 72-Hour Outage

- F1 Exam: 80 learners use their own devices to access M365. 40 learners are split into two cohorts (25 from 11:00-12:15, 15 from 12:30-13:45) using the alternate facility's 25 workstations. The IR team monitors network traffic for cheating; physical invigilators ensure exam integrity.

- F2, F3, F4, F5: Business coordinators use pre-printed forms. All manual entries require dual-authorization of maker and checker. Personal Identifiable Information (PII) must be kept in locked cabinets and later digitized securely. A manual sequential log will be used for reconciliation.

### 4.4 DR Runbook

- Facilities Clearance: COO confirms the primary site is unsafe; activate alternate site (08:00 - 09:00).

- Network & Auth: Tech 1 restores network, then AUTH01 (08:00 - 09:00).

- Security Checks: Tech 1 performs security checks (09:00 - 09:30).

- DB01 & FS01: Tech 1 restores DB01 (09:30 - 11:00). Tech 2 restores FS01 (09:30 - 10:30).

- App Restoration: Tech 1 restores LMS01 (11:00 - 11:45); Tech 2 restores FIN01 (11:00 - 11:30).

- Validation & Acceptance: Business leads validate data and sign off. Rollback: If DB01 integrity fails, revert to the Day -3 offline backup and accept data loss, notifying the COO.

### 4.5 Stakeholder Communication & Learner Notice

Initial Learner Notice:
"Dear Northbridge Learners, due to severe flooding and power failure at our main site, campus facilities are closed for the next 72 hours. Your safety is our priority. For the 120 learners scheduled for the 11:00 examination: 80 of you will receive an email via Microsoft 365 with a secure link to take the exam remotely on your own devices. The remaining 40 learners requiring centre workstations must attend the Alternate Facility. To manage capacity, you will be assigned to two cohorts: Group A at 11:00, and Group B at 12:30. Bring valid ID. Invigilators will enforce strict assessment integrity protocols. All other classes and services are suspended. Fee and admission deadlines will be handled via manual processing. Kindly await further instructions. We appreciate your patience and will provide updates by email."

IR Trigger:

The detection of an unexpected backup administrator logon during recovery triggers immediate IR involvement, as it indicates a potential insider threat or compromised credentials.

### 4.6 Return to Primary Site

Facilities must clear the site for safety. The technical team will sync manual records to the restored systems. Business validation must occur before final sign-off by the COO.

Task 5: Recovery Schedule and Exercise

# 5.1 Modelled Baseline Schedule 2 Technicians

Prerequisites dictate the sequence. Net -> AUTH01 -> Sec -> DB01 -> Apps. FS01 requires AUTH01 + Sec.

| Time | Action | Technician | Prerequisite | Finish Time |
| --- | --- | --- | --- | --- |
| 08:00 - 08:30 | Recovery Network | Tech 1 | None | 08:30 |
| 08:30 - 09:00 | AUTH01 Restoration | Tech 1 | Network | 09:00 |
| 09:00 - 09:30 | Security/Backup Checks | Tech 1 | AUTH01 | 09:30 |
| 09:30 - 11:00 | DB01 Restoration | Tech 1 | Security Checks | 11:00 |
| 09:30 - 10:30 | FS01 Restoration | Tech 2 | AUTH01 + Sec Checks | 10:30 |
| 11:00 - 11:45 | LMS01 Restoration | Tech 1 | DB01 | 11:45 |
| 11:00 - 11:30 | FIN01 Restoration | Tech 2 | DB01 | 11:30 |
| 11:45 - 12:15 | REG01 Restoration | Tech 1 | DB01 | 12:15 |
| 11:30 - 12:15 | HR01 Restoration | Tech 2 | DB01 | 12:15 |

- Earliest F1 Restoration: 11:45 (Elapsed: 3 hours 45 minutes). Controls assessment finish time.

- All Functions Complete: 12:15 (Elapsed: 4 hours 15 minutes).

- RTO Comparisons: F1 (3h 45m) misses the 2.5h RTO. This confirms the 11:00 exam must use the continuity workaround. F2 (3h 30m) meets the 6h RTO. F3 (4h 15m) meets 8h. F4 meets 24h. F5 (2h 30m) meets 48h.

- RPO Comparisons: DB01 restored to 07:00 (1-hour loss) - meets RPO. AUTH01 restored to 00:00 (8-hour loss) - misses F1's 1h RPO; manual reconciliation is required for AUTH01.

5.2 Tabletop Exercise (45 Minutes

| Time | Inject the | Decision & Revised Action | Owner | Rationale | Effect on Service |
| --- | --- | --- | --- | --- | --- |
| Min 10 | Closure extends to 5 days | Activate long-term remote learning. Dispatch manual payroll via bank portal. | COO | 72-hour plan insufficient for 5 days. | Sustained operations but requires overtime pay for staff. |
| Min 20 | Only 15 workstations available | Stagger exam into 3 cohorts (15, 15, 10). Ask 80 BYOD learners to share hotspots. | Dean | Maintains exam integrity; prevents overcrowding. | Exam finishes by 15:00 instead of 11:45. |
| Min 30 | DB01 incremental fails; Admin logon detected | Trigger IR. Isolate network. Do not restore corrupted data. Roll back to Day -3 offline backup. Force password reset on all admins. | IT/IR Manager | Prevents ransomware propagation; secures environment. | F1-F4 data loss increases to 3 days. Massive manual reconciliation needed. |
| Min 40 | Provider shows payments missing locally | Suspend automated receipting. Manually reconcile via provider portal. Dual-sign all temporary receipts. | Finance Dir | Ensures financial integrity and prevents fraud. | Delays fee confirmations; learner accounts temporarily locked. |

### 5.3 Corrective Actions

| S/N | Action Item & Description | Priority | Owner | Target Date | Measurable Completion Evidence |
| --- | --- | --- | --- | --- | --- |
| 1 | Implement immutable with separate admin credentials to address the shared identity vulnerability and ensure access independence. | High | IT/IR Manager | 30 days | Provide configuration audit logs and an access control matrix proving separation of duties and immutability. |
| 2 | Procure a mobile generator/UPS for the alternate site to support more workstations and mitigate power risks at the backup facility. | High | Facilities HOD | 60 days | Purchase order, installation certificate, and successful load test report. |
| 3 | Update exam policy to include BYOD and staggered cohort protocols and train invigilators on the new procedures. | Medium | Dean of Academics | 14 days | Updated policy document published; signed relevant document. |

# Task 6: Governance and Performance Measures

### 6.1 Plan Ownership and Approval

Clear governance ensures accountability. The table below outlines the roles and responsibilities for the BC/DR plan.

| S/N | Role | Assigned To | Responsibilities and Authority |
| --- | --- | --- | --- |
| 1 | Plan Owner | BC/ DR Manager | Ultimate authority to activate the plan during a crisis, maintain it day-to-day, coordinate updates, schedule tests, ensure training occurs, and manage the corrective action register. |
| 2 | Executive Approver | Chief Executive Officer (CEO) | Approve budget expenditures and sign off on residual risks. |
| 3 | Business Unit Leads | Dean, Finance Dir, Registrar, HR Dir, Records Manager | Responsible for validating business requirements, executing manual workarounds, and signing off on data integrity after restoration. |
| 4 | Technical Recovery Team | 2 IT Technicians | Execute the DR runbook, restore systems, perform integrity checks, and report technical status to the Plan Owner. |

6.2 Risk-Based Testing Calendar, Triggers, and Maintenance

To prevent outdated, inefficient plans and ensure readiness, the following lifecycle management schedule is recommended.

| Governance Component | Proposed Schedule | Details & Requirements |
| --- | --- | --- |
| Testing Calendar | Quarterly: Tabletop Exercises Semi-Annual: Backup Restoration Tests Annual: Full Simulation / Parallel Test | Risk-based approach focusing on the highest-impact functions (F1 & F2) more frequently. Tests are scheduled during low-impact academic periods (e.g., holidays). |
| Review Triggers | Event-Driven | Mandatory plan review triggered by: Major infrastructure changes, new software deployments, organisational restructuring, facility relocation, or after any actual disaster activation. |
| Training | Annual & Role-Specific | Annual general awareness for all staff. Semi-annual role-specific training for the Crisis Management Team, IT technicians, and Business Unit Leads on manual workarounds. |

### 6.3 Framework Alignment: NIST SP 800-34 and ISO 22301

The table below maps the deliverables created in this report to the core planning steps of NIST SP 800-34 and the relevant applicability of ISO 22301.

| Framework | Framework Step / Theme | Mapped Output from this Report | Justification |
| --- | --- | --- | --- |
| NIST SP 800-34 | Step 1: Develop Contingency Planning Policy Statement | Task 4: Scope, Activation, and Roles | Establishes the formal boundaries, activation thresholds, and authority (COO) for initiating the plan. |
| NIST SP 800-34 | Step 2: Conduct Business Impact Analysis (BIA) | Task 1: Five-Function BIA & Worked Calculations | Correlates critical systems to mission processes and quantifies the financial and operational impact over time. |
| NIST SP 800-34 | Step 3: Create Contingency Strategies | Task 3: Recovery Strategy & Budget | Evaluates and selects the Warm Site strategy based on BIA findings, balancing cost against recovery speed. |
| NIST SP 800-34 | Step 4: Plan Testing, Training & Exercises (TT&E) | Task 5: Recovery Schedule & Tabletop Exercise | Validates the baseline schedule, tests the team via stress injects, and generates measurable corrective actions. |
| ISO 22301 | Clause 5: Leadership | Task 4: RACI Matrix & Task 6: Ownership | Demonstrates executive commitment through the COO's approval role and a clear RACI matrix defining accountability. |

### 6.4 Climate and Flood Consideration

The ISO 22301:2019 Amendment 1:2024 provides for Climate action changes, organizations must evaluate the physical risks of climate change. For Northbridge Skills Institute, the primary threat is severe flooding.
Mitigation Measure: The institute must conduct a dedicated flood risk assessment to ensure the new alternate facility is geographically elevated and situated outside the floodplain. Furthermore, the primary site's local server room that has AUTH01 and DB01 must be relocated from the ground floor to an upper level, with raised flooring and water sensors installed to prevent physical hardware destruction during future flood events.

### 6.5 Key Performance Indicators (KPIs)

The following metrics will be reported to the COO every quarter to measure program effectiveness.

| KPI | Measurement Method / Formula | Data Source | Target | Frequency | Accountable Owner |
| --- | --- | --- | --- | --- | --- |
| Recovery Performance | (Number of functions restored within RTO / Total functions restored) × 100 | Exercise/Downtime Reports | ≥ 90% | Quarterly | BC/DR Manager |
| Restoration-Test Coverage | (Number of critical systems successfully test-restored / Total critical systems) × 100 | Backup Logs & Test Reports | 100% | Semi-annual | BC/DR Manager |
| Corrective Action Closure | (Number of corrective actions closed on target date / Total actions assigned) × 100 | CAPA Register | 95% | Monthly | COO |
| Training Completion | (Number of staff completing BC/DR training / Total staff required to train) × 100 | LMS Training Records | 100% | Annual | HR Manager |

### 6.6 BC/DR Maturity Assessment

- Current State: Level 2 Developing and Repeatable. Northbridge has basic plans for critical systems and some reliance on individual technical experts. (e.g., the 2-technician dependency). Testing has historically been irregular.

- 12-Month Improvement Target: Level 3 Defined and Standardised.

- Action Plan: To reach Level 3, the institute will standardise its recovery processes using the runbook established in Task 4, implement the regular testing calendar, and ensure a clear, documented governance chain of command so that recovery is not dependent on specific staff members being present.

# References

- ICDFA. (2024). Business Continuity and Disaster Recovery. GRC205, Week 21. Teaching slide.

- ICDFA. (2024). Incident Response Planning. GRC205, Week 20. Teaching Slide.

- ISO (2019) ISO 22301:2019 Security and resilience – Business continuity management systems – Requirements. Geneva: International Organisation for Standardisation.

- ISO (2024) ISO 22301:2019/Amd 1:2024 Climate action changes. Geneva: International Organisation for Standardisation.

- NIST (2010) SP 800-34 Rev. 1: Contingency Planning Guide for Federal Information Systems (updated November 2010). Gaithersburg, MD: National Institute of Standards and Technology

- AI Assistance Acknowledgement: Deepseek AI was utilised to assist with research and structuring the tables and matrices. All AI-assisted work was reviewed and verified.